## Overall Schedule
| Delivery Date to EC (Proj. Month) | Delivery Date to EC | Del. No. | Deliverable Name | WP No. | WP Leader | Lead Participant | Lead Beneficiary | Nature | Dissemination Level
3 | M4 | 2014-04-30 | 1.1 | Report on selection and analysis of by-products from 1st and 2nd generation sugars | 1 | CARGILL |  | CARGILL | R | CO
3 | M6 | 2014-06-30 | 1.2 | Deliverables of 1st and 2nd generation sugars for toxicity tests | 1 | CARGILL |  | FHG | R | CO
3 | M12 | 2014-12-31 | 1.3 | Influence of side-products within 1st and 2nd generation sugars to E.coli and Aspergillus sp. for the production of BDO and IA, respectively | 1 | CARGILL |  | FHG | R | CO
3 | M14 | 2015-02-28 | 2.1 | Fermentation broth of BDO fermentation for separation and purification process in WP3 | 2 | FHG |  | MATERBIO | P | RE
3 | M14 | 2015-02-28 | 2.2 | Fermentation broth of IA fermentation for separation and purification process in WP3 | 2 | FHG |  | FHG | R | RE
3 | M24 | 2015-12-31 | 2.3 | Protocols of fermentation development for of BDO production with 1st & 2nd generation feedstocks | 2 | FHG |  | MATERBIO | R | RE
3 | M24 | 2015-12-31 | 2.4 | Protocols of fermentation development for of IA production with 1st & 2nd generation feedstocks | 2 | FHG |  | FHG | R | RE
6 | M24 | 2015-12-31 | 3.1 | Process protocols and key design parameters for scale up in WP4 for the recovery of BDO from fermentation broth | 3 | TNO |  | TNO | R | RE
8 | M24 | 2015-12-31 | 3.2 | Process protocols and key design parameters for scale up in WP4 for recovery of IA from fermentation broth | 3 | TNO |  | TNO | R | RE
9 | M24 | 2015-12-31 | 3.3 | Samples (kg scale) of IA after recovery steps for application research in WP 5 | 3 | TNO |  | TNO | P | PP
9 | M24 | 2015-12-31 | 3.4 | Process protocols and key design parameters for scale up of the purification of BDO in WP 4 | 3 | TNO |  | MATERBIO | R | RE
12 | M24 | 2015-12-31 | 3.5 | Samples (kg scale) of BDO after purification for application research in WP 5 | 3 | TNO |  | MATERBIO | P | RE
12 | M24 | 2015-12-31 | 3.6 | Process protocols and key design parameters for scale up of the purification of IA in WP 4 | 3 | TNO |  | TNO | R | RE
12 | M24 | 2015-12-31 | 3.7 | Samples (kg scale) of IA after purification for application research in WP 5 | 3 | TNO |  | TNO | P | RE
| M24 | 2015-12-31 | 3.8 | Pre-validation of the purification and separation methodology for the subsequent polymerization at small scale (up to 50 Lt) and suggestions for tuning the previous process steps based on the achieved results | 3 | TNO |  | LUBRIZOL | P | RE
12 | M42 | 2017-06-30 | 4.1 | Protocol and mass balances of feasible process up to 1 m3 | 4 | MATERBIO |  | MATERBIO | R | RE
12 | M42 | 2017-06-30 | 4.2 | Protocol and mass balances of feasible process up to 10 m3 | 4 | MATERBIO |  | MATERBIO | R | RE
15 | M42 | 2017-06-30 | 4.3 | Protocol and mass balances of feasible process up to 80 m3 | 4 | MATERBIO |  | MATERBIO | R | RE
15 | M48 | 2017-12-31 | 4.4 | Protocol of by-products valorization | 4 | MATERBIO |  | MATERBIO | R | RE
| M36 | 2016-12-31 | 4.5 | Production and delivery of first generation sugars for the 1 to 80 m3 scale production | 4 | MATERBIO |  | CARGILL | R | RE
15 | M40 | 2017-04-30 | 5.1 | Technical report on the synthesis of polyurethane from BDO, recommended path forward, commercial recommendations | 5 | LUBRIZOL |  | LUBRIZOL | R | CO
15 | M40 | 2017-04-30 | 5.2 | Technical report on the preparation of acrylic copolymers from IA, recommended path forward, commercial recommendations | 5 | LUBRIZOL |  | LUBRIZOL | R | CO
16 | M48 | 2017-12-31 | 5.3 | Report on the pilot scale latex production from IA | 5 | LUBRIZOL |  | ITACONIX | P | CO
18 | M48 | 2017-12-31 | 5.4 | Report on the development of polymeric binder system from IA | 5 | LUBRIZOL |  | TNO | P | CO
18 | M48 | 2017-12-31 | 5.5 | Report on the polymerization by polycondensation to synthesize polyesters and co-polyesters | 5 | LUBRIZOL |  | NOVAMONT | P | CO
18 | M48 | 2017-12-31 | 5.6 | Report on film applications development | 5 | LUBRIZOL |  | MIPLAST | P | CO
| M48 | 2017-12-31 | 5.7 | Report on guide formulations for biobased itaconic acid applications and results from performance tests | 5 | LUBRIZOL |  | VLCI | R | CO
18 | M6 | 2014-06-30 | 6.1 | Report describing consumer needs and market trends, including a comprehensive section on the conditions for product marketability within the CEE region | 6 | NOVAMONT |  | NOVAINST | R | PU
18 | M45 | 2017-09-30 | 6.2 | Comprehensive database with technical, economical aspects on value chain/network and unit operation level | 6 | NOVAMONT |  | NOVAINST | R | CO
20 | M45 | 2017-09-30 | 6.3 | Report describing environmental impact analysis of the process and products obtained | 6 | NOVAMONT |  | NOVAMONT | R | CO
21 | M45 | 2017-09-30 | 6.4 | Life-cycle analysis assessment following ISO 14040 and 14044 | 6 | NOVAMONT |  | NOVAMONT | R | CO
21 | M48 | 2017-12-31 | 6.5 | First steps undertaken towards products certification | 6 | NOVAMONT |  | RINA | R | CO
21 | M6 | 2014-06-30 | 7.1 | Dissemination and exploitation plan | 7 | NOVAINST |  | NOVAINST | R | RE
21 | M3 | 2014-03-30 | 7.2 | Website up and unning | 7 | NOVAINST |  | NOVAINST | O | PU
22 | M12 | 2014-12-31 | 7.3 | Leaflet on the project | 7 | NOVAINST |  | NOVAINST | O | PU
24 | M18 | 2015-06-30 | 7.4 | Halfway stakeholder workshop done, report and participants list of first workshop | 7 | NOVAINST |  | NOVAINST | O | PU
24 | M48 | 2017-12-31 | 7.5 | Final stakeholder demo event for dissemination of the projects’ results | 7 | NOVAINST |  | NOVAINST | O | PU
24 | M48 | 2017-12-31 | 7.6 | Final dissemination and exploitation report | 7 | NOVAINST |  | NOVAINST | R | RE
24 | M48 | 2017-12-31 | 7.7 | Report on Strategy and proposal for measures to be undertaken towards Standardization | 7 | NOVAINST |  | RINA | R | RE
27 | M12 | 2014-12-31 | 7.8 | IA Strategy Toolkit for Consortium Partners | 7 | NOVAINST |  | PATENTOPOLIS | R | RE
| M18 | 2015-06-30 | 7.9 | IP Strategy Set-up | 7 | NOVAINST |  | PATENTOPOLIS | R | RE
30 | M12 | 2015-06-30 | 7.10 | IP Mapping studies on 3 domains (a) itaconic acid, (b) butanediol and (c) separation/ purification technologies | 7 | NOVAINST |  | PATENTOPOLIS | R | RE
| M24 | 2015-12-31 | 7.11 | IA Management Agreement | 7 | NOVAINST | PATENTOPOLIS | PATENTOPOLIS | R | RE
30 | M24 | 2015-12-31 | 7.12 | Update of IA Strategic Plan and IP Mapping studies for developments by competitors | 7 | NOVAINST |  | PATENTOPOLIS | R | RE
30 | M36 | 2016-12-31 | 7.13 | Update of IA Strategic Plan and IP Mapping studies for developments by competitors and emerging technologies outside the Consortium | 7 | NOVAINST |  | PATENTOPOLIS | R | RE
30 | M48 | 2017-12-31 | 7.14 | Update of IA Strategic Plan and IP Mapping studies for developments by competitors and emerging technologies outside the Consortium | 7 | NOVAINST |  | PATENTOPOLIS | R | RE
30 | M18 | 2015-06-30 | 8.1 | Draft Plan for the Use and Dissemination of Foreground and periodic updates | 8 | NOVAMONT |  | PATENTOPOLIS | R | RE
33 | M36 | 2016-12-31 | 8.2 | Draft Plan for the Use and Dissemination of Foreground and periodic updates | 8 | NOVAMONT |  | PATENTOPOLIS | R | RE

## MS list
Milestone No. | Milestone Name | WP No. | Lead Beneficiary | Delivery Date | Expected Result / Assessment Criteria
M1 | Selection of 1st and 2nd generation sugars | 1 | CARGILL | M6 | List of feedstocks
M2 | Evaluation of 1st and 2nd sugars on the production of BDO and IA | 1 | CARGILL | M12 | Availability of protocols
M3 | Successful BDO and IA production with 1st generation feedstock | 2 | FHG | M14 | Availability of protocols
M4 | Successful BDO and IA production with 2nd generation feedstock | 2 | FHG | M24 | Availability of protocols
M5 | BDO crystals with desired purity for applications in WP5 | 3 | MATERBIO | M24 | Availability of protocols
M6 | IA crystals with desired purity for applications in WP5 | 3 | TNO | M24 | Availability of protocols
M7 | Proof of concept: production up to 1 m3 | 4 | MATERBIO | M42 | Availability of protocols and demo
M8 | Proof of concept: production up to 10 m3 | 4 | MATERBIO | M42 | Availability of protocols and demo
M9 | Proof of concept: production up to 80 m3 | 4 | MATERBIO | M42 | Availability of protocols and demo
M10 | Availability of 3 end-product demonstrators produced via the developed processes | 5 | NOVAMONT | M48 | Availability of prototypes (film, latex, polymeric binder system)